Proposal for

XYZ

Integrated Report FY 25|12th January, 2026

Scope of Work:

- Review Data Gap

- Assessing the maturity level and readiness of the company towards preparing an Integrated Report <IR> by:

- Review of the existing annual reports, other data presentations / data points for <IR> content elements currently present in the organization.

- Identify traditionally reported sections that may now become redundant in view of the <IR> disclosures

- Develop a three year-reporting structure

- Provide relevant benchmarks of what is required to help teams collate the reporting data require

- Timelines for preparation of <IR>

- Help set Core team

- Help in forming a ‘Core Team’ with representatives from various functions/departments

- Assist in defining the roles and responsibilities required to establish the reporting structure for <IR> within the organization to ensure oversight for the <IR> Reporting Process.

- Capacity Building

- Provide an insight into the global reporting trends

- Explain the concept of integrated reporting, value creation and the new content elements

- Identifying of corporate reporting policies and practices among global peers and suggesting a best fit content and structure for the annual report

- Conduct a session to explain the concept of <IR> and specific requirements for the development of the <IR> and walk the teams through the IIRC Framework for core team / relevant stakeholders within the organization

- <IR> Content Development

- Developing a blueprint of report structure with respect to content and data collated by the Company.

- Supporting development of <IR> sections  along with the core team at the Company, with incorporation of critical aspects such as clarity of business plan description, future orientation and linkage between different capitals.

- Conducting meetings with senior management to obtain information.

- Assisting with alignment of report content to various regulations and guidelines as well as incorporation of <IR> Framework requirements.

- We can suggest who the stakeholders would be and suggest points which could be issues for this year’s report from the materiality standpoint.

- Note: The Company will need to provide concisely the information and data which is macro and relevant and linked to its strategies, performance, risks & opportunities and outlook and the agreed data points.

- Theme & Creative rendition

- Identifying the key communication objectives of the <IR>

- Conceptualize and provide theme suggestions for the report based on the macro developments transpiring in the industry / company and the strategic focus going forward

- Theme pages

- Concept, research, writing and enhancement of content (non-financial section & <IR> pages), including the theme pages, Key Messages, Operations Review, based on the inputs provided by the company, to amply communicate the theme and the <IR> sections basis the agreed format and the data inputs shared by the company.

- Formalising the content flow and the tone of voice

- MD&A

- Design & Draft the MDA based on the agreed structure (16 Pages)

- Seek specific data and information and response to questionnaires on the industry structure, trends, opportunities, outlook, threats and challenges and precise company’s performance (based on the structure)

- Suggest sections that can be cross referenced to <IR> to avoid duplication of the information

- Note: The financial performance and ratios, risk and mitigation and very specific information on the Company’s business activities and it’s outlook that need to be provided in a concise draft to our team in the agreed formats and structure

- Development of Cover Design

- Identifying the design approach and creative rendition of the concept

- Cover design to be developed in line with the selected theme

- Design inside pages

- Narrative & IR sections to be designed in line with cover design. (116 Pages)

- Including interactive PDF

- Designing of template for Statutory and financials sections of the <IR>

- Layout of the complete secretarial and financial section (Director’s Report, Auditor’s Report, CG report, BRSR, Accounts, Notice etc.) (208 pages)

- BRSR to be shared by the client

- Financial Statements

- Designing, typesetting and art working of the complete report, composing all graphs and financial statements.

- Take on the hi-res conversion of the entire report – cover to cover – and provide  printable open files

- Creating high resolution print ready artwork in a publishing software (InDesign)

- Finalising the document for printing

- Note: We work only on final approved files

Exclusions:

| Stakeholder Engagement and Materiality Analysis -- Suggested for year Year 2/3 | - A detailed Stakeholder Engagement engaging with external large groups of internal stakeholders / large communities of external stakeholders to understand their expectations from the company / detailed external survey process with identified stakeholder groups / analysis of populated questionnaires by stakeholders is excluded. Eg engaging with external dealers, distributions channel partners, suppliers, vendors, employees, investors, communities, media, etc. |  |
| --- | --- | --- |
| Assistance with assurance -- Suggested for Year 3 |  | - Assist in coordinating with the external assurance agency including assurance visits, provide data/ information and clarifications on observations, if any, on the non-financial performance data. (This is not required in year 1 of your IR. We will be happy to engage with external consultants for year 3) |

Please note:

- Cost excludes taxes as levied by government from time to time, outstation travel / accommodation, printing charges / image purchase cost from royalty free sites and photography costs. All expenses over and above the contracted amount need to be pre-approved and supported with end vendor bills.

- Cost of additional theme pages shall be chargeable at Rs. 7,500 per page and Statutory and financial pages shall be chargeable at Rs. 1,750 per page.

- Fresh layouts will be charged at Rs 1000 per page

- Project timeline: Estimated 6 months.

- If the project is aborted at any stage for no fault of the agency, 85% of the total amount shall be payable to WP, with the remaining 15% being waived off.

- This is a document which has statutory closure deadlines, while our teams are available to assist with corrections, it is advisable to select the right team members who can support the timely and smooth closure.

- This proposal is valid for next 30 days only

Costing:

WP Communication’s charges for the above scope of work will be Rs. 13.95  lacs only + applicable taxes.

Payment terms:

- Formal Purchase order on approval & 50% advance at the start of the project

- Balance payment 15 days after the closure of the project

WP assures you of best service at all times. We trust you would find the above your satisfaction. Should you desire any further information, please feel free to contact me.

Sincerely,

CA Shailesh Vyas,

Director (Marketing)

+91 98200 67242